## Project Plan
Project Plan
Project Title: | Youth Riverbank Rehabilitation project
Start date | 2025-11-01
End date | 2026-06-01
Project phase | Activity | Start | End
Initiation & Planning
| i.e., Site identification | 2025-11-01 | 2025-11-01
| i. e., Youth engagement | 2026-01-01 | 2026-02-01
| i.e., Promotion | 2026-01-01 | 2026-02-01
Implementation
| i.e., Hold regeneration workshop x 2 | 2026-03-01 | 2026-03-01
| i.e, Conduct planting activities with young people | 2026-03-01 | 2026-03-01
Evaluation & Reporting
| i.e, Feedback surveys from attendees | 2026-04-01 | 2026-04-01
| i.e, Acquittal report completed | 2026-05-01 | 2026-05-01